## Sheet1
Project Timeline
Task | Start Date | End Date | Duration (days) | Notes
Project Proposal | 2015-01-05 | 2015-03-20 | 74 | This contains in full the reason behind the project and all of the processes that encompass it.
Documentation | 2015-01-16 | 2015-08-21 | 217 | This will a be a process of documenting all intecations and ideas associated with the project
Theorical Desiging | 2015-01-16 | 2015-02-25 | 40 | This entitles the theoretical desiging the entire system from start to finish based on models and diagrams
Testing/Confirming | 2015-01-26 | 2015-03-20 | 53 | This ecompasses testing all devices for optimum usage and parts for cofirmation on desired specifcations and proof of concept
Applicable Re-Design | 2015-03-20 | 2015-04-03 | 14 | This will comprise of taking the original deisgn and compiling all components into a fluid electrical system cabable accurate and function synthesis.
Simulating | 2015-03-27 | 2015-04-17 | 21 | This will ecompass building simulatable computer designs of all modules of the project and simulating their processes to deterime the bevaoir of these systems.
Constructing | 2015-04-10 | 2015-05-01 | 21 | This will be a process focuses on simply physically constrcuting the protoype of the system for testing and optimization
Testing/Stressing | 2015-04-24 | 2015-05-08 | 14 | This will consist of testing the device and stressing it to its local range of pheseable operation
Optimizing | 2015-05-01 | 2015-05-22 | 21 | This will aim at increasing that range of operation so as to make the device more effective and effceint
Reconfiguring | 2015-05-15 | 2015-05-29 | 14 | This will consist of taking the data from the testing and optimization and compiling it into a configuration which will be designed for implementation and final outcome
Implemeting | 2015-05-22 | 2015-08-21 | 91 | This should contain notes, concerns, or extra ideas for the task
Improving | 2015-05-29 | 2015-08-14 | 77 | This should contain notes, concerns, or extra ideas for the task
Final Testing/Confiuration Setup | 2015-08-07 | 2015-08-21 | 14 | This should contain notes, concerns, or extra ideas for the task
Finalizing Presention/Documentation | 2015-05-29 | 2015-08-21 | 84 | This should contain notes, concerns, or extra ideas for the task